## Version History
Project Name | User Management system
Module
Prepared By | A.M.perera
Version No | Version 1.0.0
Test Cycle Duration | 12/20/2023 - 12/24/2023
Test Version No | Version 1
Reviewed By | rajitha bandara
Approved By | rajitha bandara

## User
#ID | Test Scenario | Test Case | PreCondition | Action/Steps | Test Data | Expected Results | Actual Result | Status | Priority | QA Comment | QA Manager Comment
1 | Manage Sample web page | User can navigate Sample web page | Want to navigate Sample web page | 1- Copy and paste url 2- Click enter |  | Navigate to Home page | Display successful | PASS | P0
2 | Manage user Register | User can register without details | Want to register a user | 1- Open Register portal 2- Fill without details 3- Click Register |  | Display an error message | Didn't display successfully | FAIL | P1
3 | Manage user Register | User can register with only their <name> | Want to register a user | 1- Open Register portal 2- Fill with only name 3- Click Register | Lakmini | Display an error message | Display an error message | PASS | P1
4 | Manage user Register | User can register with <valid mobile number> | Want to register a user | 1- Open Register portal 2- Fill with valid Mobile Number 3- Click Register |  | Display an error message | Didn't display successfully | FAIL | P1
5 | Manage user Register | User can register with <invalid mobile number> | Want to register a user | 1- Open Register portal 2- Fill With invalid Mobile Number 3- Click Register | Invalid mobile numbers: 1- 0714477 2- 071449757256 | Display an error message | Didn't Display an error message | FAIL | P1
6 | Manage user Register | User can register with only their <valid email> | Want to register a user | 1- Open Register portal 2- Fill With valid Email 3- Click Register |  | Display an error message | Display an error message | PASS | P1
7 | Manage user Register | User can register with only their <invalid email> | Want to register a user | 1- Open Register portal 2- Fill With invalid Email 3- Click Register |  | Display an error message | Display an error message | PASS | P1
8 | Manage user Register | User can register with only their <date of birth> | Want to register a user | 1- Open Register portal 2- Fill With Date of Birth 3- Click Register |  | Display an error message | Display an error message | PASS | P1
9 | Manage user Register | User can register with only their <gender> | Want to register a user | 1-Open Register portal 2- Fill With Gender 3- Click Register |  | Display an error message | Display an error message | PASS | P1
10 | Manage user Register | User can register with only their <location> | Want to register a user | 1- Open Register portal 2- Fill With Location 3- Click Register |  | Display an error message | Display an error message | PASS | P1
11 | Manage user Register | User can register with only their <valid user name> | Want to register a user | 1- Open Register portal 2- Fill With User Name 3- Click Register |  | Display an error message | Display an error message | PASS | P1
12 | Manage user Register | User can register with only their <invalid user name> | Want to register a user | 1- Open Register portal 2- Fill With invalid User Name (User name < 3 ) 3- Click Register |  | Display an error message | Display an error message | PASS | P1
13 | Manage user Register | User can register with <valid password> | Want to register a user | 1- Open Register portal 2- Fill With Password 3- Click Register |  | Display an error message | Display an error message | PASS | P1
14 | Manage user Register | User can register with <invalid password> | Want to register a user | 1- Open Register portal 2- Fill With invalid Password (Password < 8 ) 3- Click Register |  | Display an error message | Display an error message | PASS | P1
15 | Manage user Register | User can register with <valid confirm password> | Want to register a user | 1-Open Register portal 2-Fill With valid Confirm Password 3- Click Register |  | Display an error message | Display an error message | PASS | P1
16 | Manage user Register | User can register with <invalid confirm password> | Want to register a user | 1- Open Register portal 2- Fill With invalid Confirm Password 3- Click Register |  | Display an error message | Display an error message | PASS | P1
17 | Manage user Register | User can register with unmatch password | Want to register a user | 1- Open Register portal 2- Fill With unmatch Password 3- Click Register |  | Display an error message | Didn't Display an error message | FAIL | P1
18 | Manage user Register | User can register with password and without confirm password | Want to register a user | 1- Open Register portal 2- Fill With Password and without Confirm Password 3- Click Register |  | Display an error message | Didn't Display an error message | FAIL | P1
19 | Manage user Register | User can register with all valid details | Want to register a user | 1- Open Register portal 2- Fill With all valid details 3- Click Register |  | Register successfully | Display successful | PASS | P0
20 | Manage user Register | User can register with invalid otp | Want to register a user | 1- Open Register portal 2- Fill With all valid details 3- Validate OTP with invalid OTP 4- Validate OTP |  | Display an error message | Display an error message | PASS | P1
21 | Manage user Register | User can register with valid otp | Want to register a user | 1- Open Register portal 2- Fill With all valid details 3- Validate OTP with valid OTP 4- Validate OTP |  | Navigate to Home page | Display successful | PASS | P0
22 | Manage user Register | User can resend otp | Want to resend otp | 1- Open Register portal 2- Fill With all valid details 3- Validate OTP 4- Resend OTP |  | Resend OTP | Display successful | PASS | P0
23 | Manage user Register | User can go back register page | Want to go back register page | 1- Open Register portal 2- Fill With all valid details 3- Validate OTP 4- Go Back |  | Navigate to Register page | Display successful | PASS | P1
24 | Manage Translator | User can select languages | Want to select languages | 1- Open Register portal 2- Select language Sinhala/Tamil/English |  | The words will be translated | Didn't display successfully | FAIL | P0 | Not all translations are done yet
25 | Manage user Login | User can navigate to login page | Want to login in to the web page | 1- Open Register portal 2- Click You already have an account? 3- Click Login |  | Navigate to Login page | Display successful | PASS | P0
26 | Manage user Login | User can login without details | Want to login in to the web page | 1- Open Login portal 2- Fill Without details 3- Click Login |  | Display an error message | Didn't display successfully | FAIL | P1
27 | Manage user Login | User can login with only their <user name> | Want to login in to the web page | 1 -Open Login portal 2- Fill With User name 3- Click Login |  | Display an error message | Display an error message | PASS | P1
28 | Manage user Login | User can login with only their <password> | Want to login in to the web page | 1- Open Login portal 2- Fill With Password 3- Click Login |  | Display an error message | Display an error message | PASS | P1
29 | Manage user Login | User can login with only their <invalid user name> | Want to login in to the web page | 1- Open Login portal 2- Fill With invalid User name 3- Click Login |  | Display an error message | Display an error message | PASS | P1
30 | Manage user Login | User can login with only their <invalid password> | Want to login in to the web page | 1- Open Login portal 2- Fill With invalid Password 3- Click Login |  | Display an error message | Display an error message | PASS | P1
31 | Manage user Login | User can login with only their <valid user name and invalid password> | Want to login in to the web page | 1- Open Login portal 2- With valid User name and invalid Password 3- Click Login |  | Display an error message | Display an error message | PASS | P1
32 | Manage user Login | User can login with only their <invalid user name and valid password> | Want to login in to the web page | 1- Open Login portal 2- Fill With invalid User name and valid Password 3- Click Login |  | Display an error message | Display an error message | PASS | P1
33 | Manage user Login | User can login with only their <invalid user name and invalid password> | Want to login in to the web page | 1- Open Login portal 2- Fill With invalid User name and invalid Password 3- Click Login |  | Display an error message | Display an error message | PASS | P1
34 | Manage user Login | User can login with <valid details> | Want to login in to the web page | 1- Open Login portal 2- Fill With valid details 3- Click Login |  | Navigate to Home page | Display successful | PASS | P0
35 | Manage user Login | User can login to home page | Want to login in to the web page | 1- Open Login portal 2- Fill With valid details 3- Click Login 4- Home page |  | View Home page | Display successful | PASS | P0
36 | Manage Profile | User can view profile | Want to view profile | 1- Home Page 2- Click Profile |  | View profile | Display successful | PASS | P0
37 | Manage Profile | User can logout the web page | Want to logout the web page | 1- Home Page 2- ProClick file 3- Click Logout |  | Logout the web page | Display successful | PASS | P0
38 | Manage Profile | User can close drop down list | Want to close drop down list | 1- Home Page 2- Click Profile 3- Click Cancel |  | Close drop down list | Display successful | PASS | P1
39 | Manage Home Page | User can logout the web page | Want to logout the home page | 1- Home Page 2- Click Logout |  | Logout the home page | Display successful | PASS | P1
40 | Manage Home Page | User can navigate to All Questions page | Want to navigate All Questions page | 1- Home Page 2- Scroll down 3- View Question |  | Navigate to All Questions page | Display successful | PASS | P1
41 | Manage Home Page | User can view Partners | Want to view Partners | 1- Home Page 2- Scroll down 3- View Partners |  | View Partners | Display successful | PASS | P1
42 | Manage Home Page | User can navigate to the relevant partner's page | Want to navigate the relevant partner's page | 1- Home Page 2- Scroll down 3- View Partners 4- Choose one 5- Select one |  | Navigate to the relevant partner's page | Display successful | PASS | P1
43 | Manage Home Page | User can navigate to Ask a question page | Want to navigate to Ask a question page | 1- Home Page 2- Scroll down 3- Click Ask a Question |  | Navigate to Ask a question page | Display successful | PASS | P1
44 | Manage Home Page | User can view featured questions | Want to view featured questions | 1- Home Page 2- Scroll down 3- Click Featured Question |  | View featured questions | Display successful | PASS | P1
45 | Manage Home Page | User can navigate to Hotlines page | Want to navigate to Hotlines page | 1- Home Page 2- Scroll down 3- Click Hotlines |  | Navigate to Hotlines page | Display successful | PASS | P1
46 | Manage Home Page | User can navigate to Sample social medias | Want to navigate to Sample social medias | 1- Home Page 2- Scroll down 3- Click Social Media |  | Navigate to Sample social medias | Display successful | PASS | P1
47 | Manage Home Page | User can View Here's what we offer/How it works | Want to View Here's what we offer/How it works | 1- Home Page 2- Scroll down 3- Click Sample |  | View Here's what we offer/How it works | Display successful | PASS | P1
48 | Manage Home Page | User can navigate to Ask a question page | Want to navigate to Ask a question page | 1- Home Page 2- Scroll down 3- Click Sample 4- Click Ask Question |  | Navigate to Ask a question page | Display successful | PASS | P0
49 | Manage Home Page | User can view questions | Want to view questions | 1- Home Page 2- Scroll down 3- Questions |  | View questions | Display successful | PASS | P0
50 | Manage Home Page | User can navigate to All Questions page | Want to navigate to All Questions page | 1- Home Page 2- Scroll down 3- Click Frequently Ask a question |  | Navigate to All Questions page | Display successful | PASS | P0
51 | Manage Footer | User can view the footer with details | Want to view the footer with details | 1- Home Page 2- Scroll down 3- Footer |  | View the footer with details | Display successful | PASS | P1
52 | Manage Footer | User can view latest questions | Want to view latest questions | 1- Home Page 2- Scroll down 3- Footer 4- Click Latest Questions |  | View latest questions | Display successful | PASS | P1
53 | Manage Footer | User Users can view all categories and The number of questions belonging to the category is displayed to the user. Also, you can click on the required category and view the questions | Want to view all categories and The number of questions belonging to the category is displayed to the user. Also, you can click on the required category and view the questions | 1- Home Page 2- Scroll down 3- Footer 4- Click Categories |  | View all categories and The number of questions belonging to the category is displayed to the user. Also, you can click on the required category and view the questions | Display successful | PASS | P1
54 | Manage Footer | User can search questions | Want to search questions | 1- Home Page 2- Scroll down 3- Footer 4- Search |  | Search questions | Display successful | PASS | P0
55 | Manage Footer | User can use social media | Want to use social media | 1- Home Page 2- Scroll down 3- Footer 4- Social media |  | Use social media | Display successful | PASS | P2
56 | Manage Questions | User can view questions | Want to view questions | 1- Home Page 2- Side bar 3- Click Question |  | View questions | Display successful | PASS | P2
57 | Manage Questions | User can view all questions | Want to view all questions | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question |  | View all questions | Display successful | PASS | P0
58 | Manage Questions | User can search questions | Want to search questions | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- Search |  | Search questions | Display successful | PASS | P1
59 | Manage Questions | User can ask a question | Want to ask a question | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- Click Ask Question |  | Ask a question | Display successful | PASS | P1
60 | Manage Questions | User can filter by order | Want to filter by order | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- Filter by Order |  | Filter by order | Didn't display successfully | FAIL | P0
61 | Manage Questions | User can fillter by category | Want to fillter by category | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- Filter by Category |  | Filter by category | Didn't display successfully | FAIL | P0
62 | Manage Questions | User can filter by tags | Want to filter by tags | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- Filter by Tag |  | Filter by tags | Didn't display successfully | FAIL | P0
63 | Manage Questions | User can clear filter | Want to clear filter | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- Clear Filter |  | Clear filter | Display successful | PASS | P1
64 | Manage Questions | User can display an all questions | Want to display an all questions | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- Click Questions |  | Display an all questions | Display successful | PASS | P1
65 | Manage Questions | User can view question | Want to view question | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- View Question |  | View question | Display successful | PASS | P1
66 | Manage Questions | User can view all categories and The number of questions belonging to the category is displayed to the user. Also, User can click on the required category and view the questions | Want to view all categories and The number of questions belonging to the category is displayed to the user. Also, want to can click on the required category and view the questions | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- View Categories |  | View all categories and The number of questions belonging to the category is displayed to the user. Also, click on the required category and view the questions | Display successful | PASS | P1
67 | Manage Questions | User can view most answered questions | Want to view most answered questions | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- View Most Answered Questions |  | View most answered questions | Display successful | PASS | P1
68 | Manage Questions | User can view unanswered questions | Want to view unanswered questions | 1- Home Page 2- Side bar 3- Click Question 4- Click All Question 5- View Unanswered Questions |  | View unanswered questions | Display successful | PASS | P1
69 | Manage Questions | User can ask a question | Want to navigate to Ask a question page | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question |  | Navigate to Ask a question page | Display successful | PASS | P0
70 | Manage Questions | User can ask a question with (Question characters < 10) | Want to ask a question | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question (Question characters < 10) 5- Submit Question |  | Display an error message | Display an error message | PASS | P1
71 | Manage Questions | User can ask a question without dtails | Want to ask a question | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question without dtails 5- Submit Question |  | Display an error message | Display an error message | PASS | P1
72 | Manage Questions | User can ask a question with only question | Want to ask a question | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question 5- Submit Question |  | Display an error message | Display an error message | PASS | P1
73 | Manage Questions | User can ask a question with only catagery | Want to ask a question | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Category 5- Submit Question |  | Display an error message | Display an error message | PASS | P1
74 | Manage Questions | User can ask a question with only question in details | Want to ask a question | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details 5- Submit Question |  | Display an error message | Display an error message | PASS | P1
75 | Manage Questions | User can ask a question with only question in details (Description <10) | Want to ask a question | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description <10) 5- Submit Question |  | Display an error message | Display an error message | PASS | P1
76 | Manage Questions | User can insert a picture | Want to insert a picture | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Insert Picure (.png/.jpg/.jpeg/gif) |  | Insert a picture | Display successful | PASS | P1
77 | Manage Questions | User can use bold characters | Want to use bold characters | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Bold text |  | Use bold characters | Display successful | PASS | P1
78 | Manage Questions | User can use italic characters | Want to use italic characters | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Italic text |  | Use italic characters | Display successful | PASS | P1
79 | Manage Questions | User can use underline format | Want to use underline format | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Underline text |  | Use underline format | Display successful | PASS | P1
80 | Manage Questions | User can use strikethrough format | Want to use strikethrough format | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Srikethrough text |  | Use strikethrough format | Display successful | PASS | P1
81 | Manage Questions | User can use bulleted list | Want to use bulleted list | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Bulleted List |  | Use bulleted list | Display successful | PASS | P1
82 | Manage Questions | User can use numbered list | Want to use numbered list | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description ) 5- Numbered List |  | Use numbered list | Display successful | PASS | P1
83 | Manage Questions | User can instert link | Want to instert link | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description ) 5- Insert Link |  | Instert link | Display successful | PASS | P1
84 | Manage Questions | User can remove link | Want to remove link | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Remove Link |  | Remove link | Display successful | PASS | P1
85 | Manage Questions | User can use blackqoute | Want to use blackqoute | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With Question in Details (Description) 5- Blockquote |  | Use blackqoute | Display successful | PASS | P1
86 | Manage Questions | User can ask a question with only tags | Want to ask a question with only tags | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With only Tags 5- Submit Question |  | Display an error message | Display successful | PASS | P1
87 | Manage Questions | User can submit a message | Want to submit a message | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With all details and without tags 5- Submit Question |  | Submit a question | Display successful | PASS | P0 | It takes almost 1 minute to submit a question. It is a performance issue
88 | Manage Questions | User can submit a Question | Want to submit a Question | 1- Home Page 2- Side bar 3- Click Question 4- Ask a Question With all details |  | Submit a question | Display successful | PASS | P0 | Performance issue
89 | Manage Questions | User can navigate to My Question page | Want navigate to My Question page | 1- Home Page 2- Side bar 3- Click Question 4- Click My Question |  | Navigate to My Question page | Display successful | PASS | P0
90 | Manage Questions | User can't access the settings | Don't want to access the settings | 1- Home Page 2- Side bar 3- Click Question 4- Click My Question 5- View Question 6- Settings |  | Can't access the settings | Display successful | PASS | P0
91 | Manage Hotlines | User can view hotlines | Want to view hotlines | 1- Home Page 2- Side bar 3- Hotlines |  | View hotlines | Display successful | PASS | P0
92 | Manage Translation | User can translate from English | Want to translate from English | 1- Home Page 2- Side bar 3- Hotlines 4- Click English |  | Translate from English | Display successful | PASS | P0
93 | Manage Translation | User can translate from Sinhala | Want to translate from Sinhala | 1- Home Page 2- Side bar 3- Hotlines 4- Click Sinhala |  | Translate from Sinhala | Didn't display successfully | FAIL | P0 | Not all translations are done yet
94 | Manage Translation | User can translate from Tamil | Want to translate from Tamil | 1- Home Page 2- Side bar 3- Hotlines 4- Click Tamil |  | Translate from Tamil | Didn't display successfully | FAIL | P0 | Not all translations are done yet
95 | Manage Questions | User can navigate to Ask a Question page | Want avigate to Ask a Question page | 1- Home Page 2- Side bar 3- Click Ask a Question button |  | Navigate to Ask a Question page | Display successful | PASS | P0